**Microsoft Project**

**Restrictions**

**PRACTICE EVALUATED**

**Requirements**

*Open the result file of the* ***1Av*** ***b-2020*** drive***.Mpp***

**Part 1** Restrictions

1. **Enable the summary + critical path task (Task tab+Format tab+check in** Project Summary Task, then Project tab+Format tab+check in Critical Tasks)
2. **Save Baseline**
3. **Create the following constraints (***double click on the activity + advanced eyebrow + type of restriction***):**
4. Activity ID 4 "Find new location" will now have a delimitation like "Must end on 18/12/2020
5. Activity ID 8 "Finish drawings" will now have a "Do not start after 28/12/20 20" delimitation
6. Activity ID 3 "hire architect" goesfrom 2 days to 4 days
   1. Give it permission conflict **What happened to the duration of the project?**
   2. Now remove the ID4 delimitation **What happened to the duration of the project?**
7. Activity ID 4 "Find New Location" went from 1 week to 3 days **What happened** to the  **duration of the project?**
8. Activity ID 5 "Submit proposal" wentfrom 2 days to 3 days **Or** **did something** **happen** with the  **duration of the project?**
9. Activity ID 5 "Submit Proposal" went from 3 days to 5 days **What happened to the activity "Finish ID8 Drawings"? (allow scheduling conflict)**
10. Activity ID 8 "Finish drawings" will now have a "As late as possible" delineation **What happened to the duration of the project?**
11. Activity ID 11 "Send drawings" will now have a "Do not finish before 30/01/20 21"
12. Modify ID 9 "Select outsourced" duration from 2sem to 5d **What happened to the "Submit ID11 Drawings" activity?**
13. **What happened to the project** budget**?**

**What happened to the duration of the project?**

---- End of Practice ----

XSC